## Sheet1
Task Number | Task | Assignee | Due | Dependency | Status (2/4/2019) | Status(2019/2/11) | Status(2019/2/18) | Status(2019/2/25)
1 | Dovetail -- Portal
2 | Update portal to consume VVP and VNFSDK results tarballs from parser -- what goes into portal results and what goes into application |  |  | 18 | In program | Implemented(Portal could work with VVP/VNFSDK output if this have the pass/fail) | ready to review, Panos will schedule another meeting to reivew the portal? | Done
3 | Finalize result set for application |  |  | 9, 13, 2 |  | In Progress | In Progress | Done,waiting for reviews
4 | Finalize result set for portal display |  |  | 2 |  | In Progress | In Progress | Done,waiting for reviews
5 | Provide screen shots and table of current proposed results on Dovetail Wiki |  |  | None | Done | Done | Done
6 | Provide instructions for running portal demo on Dovetail Wiki(Low priority) |  |  | None | Not done | N/A | N/A | Done https://wiki.opnfv.org/pages/viewpage.action?pageId=24576328
7 | Based on joint investigation, update portal code for VVP and VNFSDK results |  |  | 4 | TBD | In Progress | In Progress | waiting for reviews
8 | Finalize VNF portal implementation |  |  | 7 | TBD | In Progress | In Progress | waiting for reviews
VVP
9 | Investigate effort for any possible test results update to pass to VNF-SDK/VTP | Ryan to send sample results to Dovetail team | 2019-01-10 | None | Mostly Done to Integrate directly with Dovetail (pivot from original plan). | Done, ready to merge
10 | Implement ability to be triggered by VNFSDK/VTP -- Discuss on VNFSDK meeting |  | VNFSDK Meeting on 1/16/19 | None | N/A | N/A
11 | Possible update of test results format -- TBD |  |  | 12 | In progress | In progress | Done, Reviewed and ready to update according team's suggestion.
12 | Review the proposed application and display results set for the portal |  |  | 16 | Not started yet (reviewing process) | Not started yet (reviewing process) | Not started yet (reviewing process)
VNFSDK/VTP
13 | Update results reporting to provide fuller details for Dovetail information -- iterate w/ Dovetail team |  |  | None | Not started | Victor confirm with Kanag and give the timing about this | Done, ready to update according the suggestion.
14 | Possible VTP work for VVP integration (trigger/run VVP test cases from VTP) |  |  | 10 | No longer taking this approach.
Dovetail -- Test Framework
15 | Need to augment the results format to include additional fields about the test case (define a standardize format / container, etc.) |  |  | 13 | Not started for VTP, Almost done for VVP, Dovetail can consume both VTP and VVP results output (with latest patches) |  | Done, ready to update
16 | Review VVP Results Files, create plan to support consumption of results by protal | Dovetail |  | 9 | Done | Done | Done
17 | Update to differentiate btwn Tosca and Heat test case sets |  |  | 14 | Done | Done | Done
18 | Update parser to consume results and produce portal |  |  | 15, 16 | In progress | Done, ready to merge. PS: Currently the parser could covert the VVP/VNFSDK result | Done
Beta Testing
| TBD -- Dependencies on everything above except Portal |  |  |  | Not started, need companies to try running the testing (preferrably not those involved in the original test development) | Start wit Dovetail and VVP that compnies have the commercial Heat based VNF. | Refine the Doc for Dovetail, still need some information from VVP/VNFSDK. Xudan will add Trevor and Steven as the reviewer for reviewing the patch. | Done
LF Marketing/Legal
19 | Content for portal |  |  | 7 | In progress | In progress | In progress | In progress
20 | Unified landing page content |  |  | 7 | In progress | In progress | In progress | In progress
21 | Logo |  |  | None | In progress | In progress | In progress | In progress
22 | Updated Terms and Conditions |  |  | None | In progress | In progress | In progress | In progress
26 | Deploy final portals |  |  | 19, 20, 21, 8, 23, 24, 25 | In progress | In progress | In progress | In progress
Documentation
23 | Heat User Guide |  |  | None | Not started | Started, hopefully we could finish this in two weeks. | Refine the Doc for Dovetail, still need some information from VVP/VNFSDK. Xudan will add Trevor and Steven as the reviewer for reviewing the patch. | Done
24 | Tosca User Guide |  |  | None | Started in Dovetail | Started in Dovetail, hopefully we could finish this in two weeks. | Refine the Doc for Dovetail, still need some information from VVP/VNFSDK. Xudan will add Trevor and Steven as the reviewer for reviewing the patch. | Done
25 | Updates to Dovetail User Guide |  |  | 17, 2, 23, 24 | Pending above | Pending above | Pending above | Done