## Sheet1
Task Number | Task | Assignee | Due | Dependency | Status (2/4/2019)
1 | Dovetail -- Portal
2 | Update portal to consume VVP and VNFSDK results tarballs from parser -- what goes into portal results and what goes into application |  |  | 18 | In program
3 | Finalize result set for application |  |  | 9, 13, 2
4 | Finalize result set for portal display |  |  | 2
5 | Provide screen shots and table of current proposed results on Dovetail Wiki |  |  | None | Done
6 | Provide instructions for running portal demo on Dovetail Wiki |  |  | None | Not done
7 | Based on joint investigation, update portal code for VVP and VNFSDK results |  |  | 4 | TBD
8 | Finalize VNF portal implementation |  |  | 7 | TBD
VVP
9 | Investigate effort for any possible test results update to pass to VNF-SDK/VTP | Ryan to send sample results to Dovetail team | 2019-01-10 | None | Mostly Done to Integrate directly with Dovetail (pivot from original plan).
10 | Implement ability to be triggered by VNFSDK/VTP -- Discuss on VNFSDK meeting |  | VNFSDK Meeting on 1/16/19 | None | N/A
11 | Possible update of test results format -- TBD |  |  | 12 | In progress
12 | Review the proposed application and display results set for the portal |  |  | 16 | Not started yet (reviewing process)
VNFSDK/VTP
13 | Update results reporting to provide fuller details for Dovetail information -- iterate w/ Dovetail team |  |  | None | Not started
14 | Possible VTP work for VVP integration (trigger/run VVP test cases from VTP) |  |  | 10 | No longer taking this approach.
Dovetail -- Test Framework
15 | Need to augment the results format to include additional fields about the test case (define a standardize format / container, etc.) |  |  | 13 | Not started for VTP, Almost done for VVP, Dovetail can consume both VTP and VVP results output (with latest patches)
16 | Review VVP Results Files, create plan to support consumption of results by protal | Dovetail |  | 9 | Done
17 | Update to differentiate btwn Tosca and Heat test case sets |  |  | 14 | Done
18 | Update parser to consume results and produce portal |  |  | 15, 16 | In progress
Beta Testing
| TBD -- Dependencies on everything above except Portal |  |  |  | Not started, need companies to try running the testing (preferrably not those involved in the original test development)
LF Marketing/Legal
19 | Content for portal |  |  | 7 | In progress
20 | Unified landing page content |  |  | 7 | In progress
21 | Logo |  |  | None | In progress
22 | Updated Terms and Conditions |  |  | None | In progress
26 | Deploy final portals |  |  | 19, 20, 21, 8, 23, 24, 25 | In progress
Documentation
23 | Heat User Guide |  |  | None | Not started
24 | Tosca User Guide |  |  | None | Started in Dovetail
25 | Updates to Dovetail User Guide |  |  | 17, 2, 23, 24 | Pending above