## Sheet1
Task Name | Start | End | Duration (weeks) | Duration (days)
release plan agreed with all parties (Dovetail, TSC, CVC, markting) | 2018-04-18 | 2018-04-25 | 1 | 7
all test case candidates integrated in debug test suite | 2018-04-18 | 2018-05-02 | 2 | 14
test case candidates evaluated in CI (list of final candidates ready) | 2018-05-02 | 2018-06-13 | 6 | 42
pre-testing on commercial systems | 2018-05-23 | 2018-06-13 | 3 | 21
test scope agreed in Dovetail besed on passing test case candidates | 2018-06-13 | 2018-06-20 | 1 | 7
scope approved by OPNFV TSC and CVC | 2018-06-20 | 2018-06-27 | 1 | 7
documentation done (test specs, user guide, release notes) | 2018-06-13 | 2018-07-18 | 5 | 35
web portal updated | 2018-06-13 | 2018-07-25 | 6 | 42
slack | 2018-07-25 | 2018-08-01 | 1 | 7
OVP 2018.07 release | 2018-07-31 | 2018-08-01 | 0.14286 | 1